## Sheet1
[10 empty] | Isaiah absent | Playable demo | Holidays | [6 empty] | Playtest Ready |  |  |  | Final Deadline
|  | 2024-08-26 | 2024-08-28 | 2024-09-02 | 2024-09-04 | 2024-09-09 | 2024-09-11 | 2024-09-16 | 2024-09-18 | 2024-09-23 | 2024-09-25 | 2024-09-30 | 2024-10-02 | 2024-10-07 | 2024-10-09 | 2024-10-14 | 2024-10-16 | 2024-10-21 | 2024-10-23 | 2024-10-28 | 2024-10-31 | 2024-11-04 | 2024-11-06
Player | Vehicle Control | bar: 2024-08-28 to 2024-09-02
Enemy | Zombie Movement | bar: 2024-08-28 to 2024-09-02
Enemy | Zombie Spawning | bar: 2024-09-02 to 2024-09-04
Enemy | Zombie attacks | bar: 2024-09-04 to 2024-09-09
Enemy | Player Health
Player | UI | bar: 2024-09-11 to 2024-09-18
UI | Pause Menu | bar: 2024-09-16 to 2024-09-18
UI | In game currency | bar: 2024-09-04 to 2024-09-09
Gameplay | Garage/Upgrades | bar: 2024-09-09 to 2024-09-11; 2024-10-07 to 2024-10-14
Gameplay | Procedural Generation | bar: 2024-09-16 to 2024-10-07
Gameplay | Main Menu | bar: 2024-08-28; 2024-10-07 to 2024-10-14
Gameplay | Vehicle Weapons | bar: 2024-09-09 to 2024-09-11; 2024-10-07 to 2024-10-14
Player | Sound | bar: 2024-10-14 to 2024-10-21
Gameplay | Game Over | bar: 2024-09-09 to 2024-09-11
UI | Despawning world tiles | bar: 2024-09-23 to 2024-10-02
Gameplay
Playtesting/bugfixing | bar: 2024-10-28 to 2024-11-06
[5 empty] | Malachi |  |  | Neccessary for demo
[5 empty] | Isaiah |  |  | Vehicle controls
[5 empty] | Nick |  |  | Zombie movement, spawning, damaging, attacking
[5 empty] | Any |  |  | Gameover
Player health
Basic upgrades
[17 empty] | SFX | LINK
[17 empty] | clownhorn | https://pixabay.com/sound-effects/search/%20clown%20car%20horn/